## Sheet1
DATE	CLIENT	ISSUE	SERVICE	DEV	UAT	LIVE	REMARKS	RESULT	Fixed on	FIXED BY
	Edgehill-LIVE	Screenshot not shown in tickethistory tab [4]			checked by sending pics in notes for payload responses in edgehill and sunderland uat	Submitted merge request on [3-3-22]	1.checked by replying pics in notes from moses j student and staff	Need to verify		email harvesting issue - submitted merge request in live (platform-prod-uk)
	Edgehill-LIVE	1.Studiosity source to add [1] / 2. ‘’gateway on the go to remove’’		Added in enum and db	Added in enum and db	code merged, need to add in db	Waiting for testing team to confirm in uat	fixed		Added in enum and db
	Sunderland-live	apostrophy additionally added in student Id in reports [5]				Submitted merge request		fixed		fixed by changed in view
	SIT-UAT	Getting 500 when filter apply in audience page [6] (schoolNameSubcategory)		fixed and submitted merge request	fixed and submitted merge request			fixed		changed searchcriteria’s constructor’s field from String to Arraylist.asList and split() method
	SIT-UAT	Import issue - can’t import student’s in audience 360 page [7]					its done by cron based service	fixed		fixed by added industry, deparment in switch case
	Sunderland-live	Home and Student Recruitment Department name change [10]	database	checked in dev			need to change in live	fixed	08-04-2022
	Sunderland-live	Email received 2 times when export report [9]	Dynamic report		Done	fixed in uat and live .. / In live additionally added 1 configuration duplicateFix	fixed in uat and live .. / In live additionally added 1 configuration duplicateFix	fixed	06-04-2022	changed in code – set and pass campusId in pushQueue method
	cardiff	Active service 5 is not shown in calendar Service list [8]					Not an issue, it shows only for super admin	fixed
	franklin	GradingUserProgramStatus – service	Database / Arm service	Need to change in return type- to remove existing logic and remove 1 execute only one return.	1.Build done / 2. configuration written in db -select config from organization_config where type='LeaverStatus'		perfectly pushed in uat, In dev need to change	done		New service written
	Sunderland-live	categoryName shows ‘General Test Category II’ instead of covid info	database				Need to change in live db : / Replace name_path as covid info from General Test Category II or shown table should change from name_path to name	fixed	08-04-2022
	Endgehill-live	Email not sent when event created	calendar		Fixed	Done	configuration written in database for edgehill	fixed		1.get userId from calendar_invitees and set in sendCalendarQueue / 2.tokens replaced in uat, taken from live / 3. attendee_invited_registration template mapped
	Sunderland-live	The Ticket Information report has 100s of students listed as Student Type 'Student', but in the ticket they are 'old student'. Please see spreadsheet providing examples.	analytics/reports/2		SELECT ba.*,bv.display_name,bv.actual_name,bv.description as view_description,bv.module FROM bi_analytics ba left join bi_view bv on ba.view_id = bv.id where ba.id = 1		In dev – userTypeName fixed based on ticket.user_id and user_type_id / In sunderland Report – userTypeName fixed based on ticket.old_student_name	processing
08-04-2022 [FRI]	Luton -uat , Live	In staff – Alphabatic order name searching not working – it returns first name’s last letter instant of first name’s first letter			changed whereParamClause to generateWhereClause , return type and comment params field in findAll and count method		Build done	fixed	11-04-2022
11-04-2022 [Mon]	Edgehill-LIVE	Need to show particular teams in ticket and case transfer		added source column in team_master table	1.added source column in team_master table / 2.Added field source in pojo and field		Frontend need to pass payload as source = ticket or case	fixed
12-04-2022 [TUE]	SIT-UAT	Email not received for mentor, when mentor assigned	communities/mentorMenteeProgramRelationDump/{programId}{mentorId}/{menteeId}		1. added mentorEmail configuration / 2. interchanged tokens		Atlast inter-changed name and assignedUserName	fixed		1.Assigned mentorId in program_recipients in execute query with configuration / 2.Added relation_type in query / 3.interchanged name and assignedusername tokens in mentor matching template
21-04-2022 [THUR]	SIT-UAT	When campaign create – added receipient count mistakes	admin/audience/audienceStatistics					fixed	20-04-2022	Additionally 5 students are added in recipients for alumni --- code have configuration But not in db .. so added in db alumniSITConfig
26-04-2022 [TUE]	SIT-UAT	mentor mentee registration form view issues / 1. registration form shows personal Email as super Admin’s								changed in dynamic form and published, and taken version from from df_pages (form_id column) and copied into uat’s df_pages
29-04-2022 [FRI]	SIT-UAT	1. preferred mentor not shown / 2. preferred name not shown in mentor form / 3. matric number and mobile no not shown in mentee form / 4. in mentee registration form - to remove default personal email / 5. pdpa checkbox

eversity	groups update count	1.userRecord api counts adds existing criterias / 2. need to pass removed criterias userIds in userId keys when update